## Module Plan
S.No | Module | Description | Hours
1 | Module 1: Authentication & User Registration | Rebuild standardized database | 2
2 |  | Set up project structure & auth routes | 1
3 |  | Build login, forgot password and registration forms | 2
4 |  | Build validations for login, forgot password and registration | 2
5 |  | Implement failed login attempt counter + deactivate logic | 1
6 |  | JWT token generation + redirect to dashboard | 1
|  | Total | 9
7 | Module 2: Navigation & Layout | Create top navigation bar (basic links) | 2
8 |  | Style navigation bar (responsive design) | 1
9 |  | Add profile icon + dropdown (logout option) | 2
10 |  | Implement logout functionality | 1
11 |  | Route guards (check auth, redirect unauthenticated) | 2
|  | Total | 8
12 | Module 3: User Profile | Build editable form for user details | 2
13 |  | Backend update logic for user details | 2
14 |  | Profile picture upload (frontend form + backend API) | 2
15 |  | Sync avatar across navbar/profile page | 1
16 |  | Testing + validation of profile updates | 1
|  | Total | 8
17 | Module 4: Admin Panel | Create admin-only route + layout | 2
18 |  | Build user list table (fetch + display users) | 2
19 |  | Implement activate/deactivate toggle | 2
20 |  | Role-based route guard (admin only access) | 1
21 |  | Testing + validation of admin actions | 1
|  | Total | 8
22 | Module 5: Chat Module | Setup SignalR connection | 2
23 |  | Build chat UI (message input + display) | 2
24 |  | Implement file attachment upload/download | 2
25 |  | Load message history from DB on open | 1.5
26 |  | Online/offline presence indicator | 1.5
|  | Total | 9
27 | Module 6: Enhancements & Testing | Implement “remember me” with cookies | 2
28 |  | Server-side session handling | 2
29 |  | Custom middleware (auth header validation) | 1.5
30 |  | Error handling improvements | 1
31 |  | Unit test one service with xUnit | 2
|  | Total | 8.5